## Sheet1
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Topic Decided | bar: Week 1
Project Plan Completed | bar: Week 1 to Week 2
Project Design | bar: Week 1 to Week 2
PsudeoCode | bar: Week 2 to Week 3
Development Commences | bar: Week 2 to Week 10
First Working Prototype | bar: Week 5
Any updates required | bar: Week 5
Testing of Updated Prototype | bar: Week 5 to Week 6
Finalised Project | bar: Week 11 to Week 12
Final Group Report | bar: Week 11 to Week 12