## Sheet1
TimeLine | Start Date | End Date | Duration | Contributor
Project Discussed | 2021-02-03 | 2021-02-05 | 2 | All Group
Application Requrierments | 2021-02-03 | 2021-02-05 | 2 | All Group
Psuedocode Designed | 2021-02-03 | 2021-02-05 | 2 | Cian
Database Designed | 2021-02-03 | 2021-02-05 | 2 | Daniel
Discussion about implementation | 2021-02-03 | 2021-02-06 | 3 | All Group
Repository Inatialisation | 2021-02-03 | 2021-02-06 | 3 | Ryan
CSV File Created | 2021-02-10 | 2021-02-12 | 3 | David
Knockout Stage Class Created | 2021-02-15 | 2021-02-20 | 5 | Ryan
Tournament Class Created | 2021-02-15 | 2021-02-22 | 7 | Cian
Team Class Created | 2021-02-15 | 2021-02-24 | 9 | Daniel
Randomiser Class Created | 2021-02-15 | 2021-02-26 | 11 | David
System Testing | 2021-03-01 | 2021-03-04 | 3 | Cian
Application testing | 2021-03-01 | 2021-03-04 | 3 | David
Intigration Testing | 2021-03-01 | 2021-03-04 | 3 | Ryan
First Prototype | 2021-03-08 | 2021-03-10 | 2 | All Group
Resolving any issues | 2021-03-11 | 2021-03-12 | 1 | All Group
Implenting any changes required | 2021-03-15 | 2021-03-19 | 4 | All Group
System Testing | 2021-03-20 | 2021-03-23 | 3 | Cian
Application testing | 2021-03-20 | 2021-03-23 | 3 | Daniel
Intigration Testing | 2021-03-20 | 2021-03-23 | 3 | David
Updates and fixes | 2021-03-24 | 2021-03-31 | 7 | All Group
finalised Prototype | 2021-04-01 | 2021-04-05 | 4 | All Group
Finalised Report | 2021-04-08 | 2021-04-09 | 1 | All Group
Submissions | 2021-04-09 | 2021-04-10 | 1 | All Group